## Project Plan
Week Commencing | Action | Action Owner | Status | Notes
2018-09-03 | Finalise V2 of M3 questionnaire | Ben, Colin, Paul | Complete | Questionnaire refined and shortened based on feedback from V1
| Create online version of M3 questionnaire V2 | Colin | Complete | Link to online survey: https://understandingexpertise.uk/index.php/144319?lang=en
| Collate feedback from Summit Video | Paul | Blocked | Summit video is not available
| Create briefing pack for development of online application | Paul | Complete | Use cases split into phase 1 to deliver minimum viable product by Measurement Month followed by additional functionality in phase 2 (timescale TBC)
2018-09-10 | Output of V2 questionnaire to be shared with Aseem | Colin | In progress | To support planning of AsiaPac chapter M3 event for measurement month
| Identification of current technology stack for AMEC website / IEF | AMEC executive | Complete | IEF uses WordPress. Recommendation to augment this with database management system (eg mySQL) to handle number crunching
| Identification of available budget for M3 development | AMEC executive | Complete | Solution scoped at c.10 days development at a cost of £4k. Blaze should be able to support as part of existing maintenance contract
2018-09-17 | Identification of development resource | AMEC executive / M3 team | Complete | Mike Ishmael who supported the IEF development is able to do the development in October
| Development resource to be briefed on online application | Paul | Complete | Paul has briefed Mike about scope and has passed on briefing documentation
| Scoping of technology stack and solution | Mike Ishmael / Blaze | Complete | Mike has spoken to Andrew from Blaze - plan is to create new subdomain that will give us new instances of WordPress for the webpages and MySQL for the database
| Go ahead from AMEC executive based on agreed scope and budget | AMEC executive | Complete | Budget is £4k, scope as per Phase 1 from briefing document
| Translation of piliot questionnaire data into V2 questionnaire and data structure | Paul | Complete | Paul has built and populated new data tables passed onto Mike in spreadsheet form
| Topline application design | Mike Ishmael | In progress
2018-09-24 | M3 online application development | Mike Ishmael | In planning | c.10 days of development time spread over six weeks
2018-10-01 | M3 online application development | Mike Ishmael | In planning
2018-10-08 | M3 online application development | Mike Ishmael | In planning
2018-10-15 | M3 online application development | Mike Ishmael | In planning
| Text and imagery for M3 landing page | Ben | In progress
2018-10-22 | M3 online application development | Mike Ishmael | In planning
2018-10-29 | M3 online application testing and hosting on main site | Mike Ishmael / Blaze / Paul | In planning
2018-11-05 | M3 online application sign-off | AMEC executive / M3 team | In planning
2018-11-12 | M3 event for Asia Pacific Chapter (timing TBC) | Aseem | In planning | Timings and format to be agreed by Aseem
2018-11-19 | Measurement Month PRCA event | Ben, Paul | In planning
| Measurement month PRWeek event | Paul, Colin | In planning
2018-11-26 | Additional marketing promotion for M3 application (TBC) | AMEC executive / M3 team | In planning